## Sheet1
Date | Name 1 | Name 2 | Name 3 | Name 4 | Overall Status
| Ujwal N M | Maria Antony | Vijay Patil | Sakunthala PL
2021-04-09 | Completed Sequence Diagram | Completed Sequence Diagram | Completed Sequence Diagram | Completed Sequence Diagram | Completed all the microservice, Working on MVC completed. Consuming the API in MVC also completed.
| Completed Authorization Microservice | Completed AuditSeverity Microservice | Completed Audit Checklist Microservice | Completed Audit Benchmark Microservice
| Completed Audit Portal MVC | Working on Integration | Working on Integration | Working on Integration
2021-04-10 | Completed Nunit testing for Authorization Microservice | Completed Nunit testing for AuditSeverity Microservice | Working on Nunit testing | Completed Nunit testing for Audit Benchmark Microservice | Pending with Nunit testing for Audit Checklist Microservice
2021-04-12 | Worked on the required changes in MVC, Completed Nunit testing, Working on depoyment | Worked on the required changes in API, Completed Nunit testing, Working on depoyment | Worked on the required changes in API, Completed Nunit testing, Working on depoyment | Worked on the required changes in API, Completed Nunit testing, Working on depoyment | Completed Nunit testing, Working on deployment
2021-04-14 | Working on cloud deployment | Working on cloud deployment | Working on cloud deployment | Working on cloud deployment | Working on cloud deployment
2021-04-15 | Working on cloud deployment | Working on cloud deployment | Working on cloud deployment | Working on cloud deployment | Pipeline waiting for agent allocation in Azure
2021-04-16 | Working on final presentation | Working on final presentation | Working on final presentation | Working on final presentation | Working on final presentation
2021-04-17 | Final presentation ppt completed | Final presentation ppt completed | Final presentation ppt completed | Final presentation ppt completed | Final presentation ppt completed